## Blad1
Project TB-RAM CoE
Evaluation of developed hardware and software solutions
Component | Type | Development group
Robot control program (Print3D) | Software | Dennis Bengs, Bart Blaster
Problem | Solution | Implementation
The core of the additive manufacturing process is the master control program. This program translates machine code into real-world actions. Conventional 3D printers use firmware such as Marlin to translate G-Code into printer commands. Such printer firmware is not compatible with robotic arms. In addition, the requirement to control an external extruder firmware further complicates the problem. | A robot control program is required to translate machine code into both robot and extruder actions. The robot program would require sophisticated features such as touch probe integration, extruder synchronization, heater control, error checking and much more. | A robot control program nicknamed Print3D was developed over the course of the project. The program grew in complexity as more and more features were required, as well as when adding support for newly developed hardware. The program was written in ABB RobotStudio in the RAPID programming language. The programmed was evalulated inside the RobotStudio robot Digital Twin for safety reasons.
Result | What went right? | What went wrong/Could be improved?
The program started off fairly rough, with support for only a small subset of the machine code used by conventional 3D printers. Over the project we kept improving the program, adding support for missing commands. The extruder synchronization was improved which in turned improved the quality of manufactured objects. Support for mesh bed leveling was added, as well as resume-on-error. The final program is reliable and fault-tolerant, and will run on conventional 3D printer machine code. | Over the course of the project, there has not been a single robot crash due to the program. The synchronization improvements greatly improved the quality of manfactured objects. The bed leveling routines worked flawlessly. | The synchronization could have been improved further by connecting a digital output to the extruder, or by controlling the extruder through an external axis. A lot of time went into debugging and solving the issue. A lot of prints failed due to errors in the robot operating system. This issue was eventually solved with the resume-on-error feature.
Component | Type | Development group
Extruder control program (xstrudt) | Software | Novia
Problem | Solution | Implementation
The extruder tool is a complex piece of hardware which requires its own microcontroller and firmware to run. | A custom firmware is required to control all the components of the extruder tool. This firmware needs to be able to manage the heater temperature, the extrusion distance, touch probe deployment and probing; and error conditions. | An Arduino firmware called xstrudt was adapted and developed further based on an older firmware. The firmware has been mostly re-written, with a large number of additional features being added. The messaging protocol between the robot and the firmware was extended to allow more data to be transmitted per message. Additional error checking was added to handle almost every error condition.
Result | What went right? | What went wrong/Could be improved?
The final firmware is stable, customizable and has much improved error reporting, allowing easier debugging of print issues. The touch probe integration works great. The extruder resolution was greatly improved to further improve the print quality. | The extruder has great error handling, which makes it relatively safe to use. | The firmware has had a number of bugs which were relatively difficult to debug. The filament extrusion distance calibration procedure should be improved, as this part was especially troublesome.
Component | Type | Development group
Extruder tool | Hardware | UWASA/Novia
Problem | Solution | Implementation
An extruder is the part which melts and extrudes molten filament in additive manufacturing. Such tools are commonly used together with dedicated 3D printers, but are not often used with robotic arms. A custom made extruder design is required. | A custom-made extruder tool is required with special considerations for robotic additive manufacturing. The extruder needs to be designed to work with freeform printing, and to be mountable on a robot arm. | The extruder tool was designed and iterated upon over the course of the project. Several re-designs took place as we discovered new issues with the old designs, and as we required new features to be added to the extruder.
Result | What went right? | What went wrong/Could be improved?
The final extruder tool has a number of useful features. It is streamlined and pointed to allow for freeform printing. It has a compressed air cooling system. It allows for bed leveling using a retractable touch probe system. It is mostly 3D printed and can be upgraded/repaired easily. | The final version of the tool works very well, is easy to attach/detach from the robot, and has shown to be a very reliable and easy to repair when something breaks. | The tool has gone through several iterations, with a large number of different failures. The spring-loading system, while a good idea in theory, turned out to be very difficult to implement. The earlier versions of the extruder tool had various problems, such as the entire extruder rotating due to the center clamp not being tight enough.
Component | Type | Development group
Extruder tool - Robot mount | Hardware | UWASA/VAMK
Problem | Solution | Implementation
Robots arms are multipurpose tools which can perform a great number of different tasks. A requirement for quick and easy re-purposing is that the tools used by the robots can be removed and interchanged swiftly. A tool which is tightly integrated with the robot takes a long time to remove and makes the robot less versatile. | A special mount is required for the extruder tool to make it easy to attach and detach from the robot arm. | The extruder tool was designed to connect to the plates used by the pneumatic tool changing system used by the ABB IRB-1200 Robot. The extruder tool is attached to the plate using screws. The plates can be locked and released from the last robot joint using pneumatic signals.
Result | What went right? | What went wrong/Could be improved?
The robot mount allowed the extruder tool be attached and dettached from the IRB-1200 robot in a manner of minutes, allowing the robot to be shared between multiple groups with relative ease. | The mounting plate allowed for quick and easy tool replacements for the robot. It was quick and easy to use. | The earlier extruder tool version was controlled through a connector embedded in the mounting plate. The intended purpose of this connector is to make it easier to connected electric signals to the connected tool. This ended up being too complicated in a shared environment as the cables kept getting in the way.
Component | Type | Development group
Extruder tool - Touch probe and servo | Hardware | UWASA
Problem | Solution | Implementation
Having a consistent height on the first layer is very important during additive manufacturing. If the build platform is warped, this may be impossible to achieve using a basic coordinate system definition. | Some form of sensor is required to allow the bed height to be automatically adjusted in the robot control program. | After studying a large number of different probing solutions, we decided to go with a BLTouch 3D printer probe as the bed leveling sensor. Due to requirement to have a pointed shape of the extruder tool, we also designed a retractable mount for the touch probe to allow the probe to be moved out of the way during printing.
Result | What went right? | What went wrong/Could be improved?
The extruder tool has a retractable bed leveling probe allowing the robot to automatically scan the build platform for height inconsistencies and curvature. The robot control program is then able to compensate for these inconsistencies. | The retractable bed leveling probe worked extremely well, even at the first test. After calibrating the height between the nozzle and the touch probe, the first printed layer had a height error of around 50 microns, which is within the required tolerance. | While the touch probe allows for quick bed leveling, the height between the touch probe and the hot end nozzle needs to be calibrated manually. This has to be done each time the nozzle is adjusted in any way, such as when the hot end is removed for any reason.
Component | Type | Development group
Extruder tool - Compressed air cooling system | Hardware | UWASA
Problem | Solution | Implementation
The traditional way of cooling the hot end and printed layer during additive manufacturing is to use fans mounted on the extruder tool. This setup is both large and not very efficient. | A more compact and efficient cooling system is required for the extruder tool. | The compressed air cooling system was designed as a separate detachable component which attached to the extruder tool heatsink. The airflow through the interior tubing and openings was simulated and optimized to reduce air noise. A large number of variations of the part were printed and tested to find the best and most silent design. Air flow regulators were installed to control regulate the air flow.
Result | What went right? | What went wrong/Could be improved?
The extruder tool has an air cooling system which provides cooling for both the hot end heat sink, and for the printed part through smaller longer air tubes. The air flow can be regulated to provide the optimal air flow for cooling the heatsink and part. | The compressed air cooling system is extremely powerful, and can provide way more cooling than the current setup could ever need. The air flow regulators provide a convenient way to control the air flow with the twist of a knob. | The first version of the air cooling system was very loud due to the way strong air flows create a lot of noise. It took many attempts to find a design which reduced the noise to an acceptable level.
Component | Type | Development group
Extruder tool - Microcontroller housing | Hardware | UWASA
Problem | Solution | Implementation
The microcontroller controlling the extruder works with relatively large voltages and can be dangerous if left exposed. The microcontroller can also overheat and may require additional cooling to remain safe. | Some type of housing is required for the extruder tool microcontroller. | A new type of microcontroller housing for the MKS Gen 1.4 microcontroller was designed from scratch and 3D printed. The housing cable openings for optimized to minimize the amount of wires required inside the housing. A fan was installed at the top cover to provide cooling for the stepper drivers, as they have a tendency to overheat and burn out.
Result | What went right? | What went wrong/Could be improved?
The new microcontroller housing attaches to the back of the robot and holds the MKS Gen 1.4 microcontroller for the extruder tool. The microcontroller connects to the extruder tool through a flexible cable connection. The housing protects the robot and people from accidentally touching live wires, and the installed fan provides cooling and prevents overheating. | The housing has a convenient design which allows easy access to the microcontroller if the need arises. The installed lights allows for an easy check for extruder issues. | The extruder housing could potentially have been made even more compact, as there is still a lot of empty space inside. The cable and cover latches are too loose due to the inflexibility of PLA plastic.
Component | Type | Development group
Extruder tool - Cable connection | Hardware | UWASA
Problem | Solution | Implementation
The connection between the microcontroller and the extruder tool must be both reliable and easy to remove. The extruder tool and robot is constantly moving which makes the choice of connection crucial. | A reliable communication path is required between the extruder tool microcontroller and the extruder tool. | After researching the issue and looking at different alternatives, a flexible cable was selected specifically for its robustness and matching number of leads. Connectors were installed on the cable to allow it to be removed.
Result | What went right? | What went wrong/Could be improved?
A flexible cable connects the extruder microcontroller to the extruder tool by clamping the cable to the side of the robot. | Being able to quickly remove the cable turned out to be invaluable, as it allows the microcontroller and extruder tool to be separated individually. | A smaller cable could have been used, as the cable leads have a larger diameter than is strictly necessary for the maximum load.
Component | Type | Development group
Extruder tool - Spring loading | Hardware | UWASA
Problem | Solution | Implementation
Due to the wobble caused by the translation of linear paths to joint paths with robot arms, the hot end may move up and down across a printed layer. This can cause robot crashes in the worst case scenario. | Some form of safety mechanism is required to avoid robot crashes to to vertical wobble. | Several versions of a spring loading mechanism were designed and tested with the extruder tool. The spring loading is put between the extruder gear and the heatsink, and allows the heatsink and hot end to be pushed up about 4-5 millimeters without damage.
Result | What went right? | What went wrong/Could be improved?
We were unable to get the spring loading to work as intended. Due to the small movement distance of the spring, a relatively large amount of horizontal movement of the hot end was possible. These movements were larger than what could be allowed during the printing process. The spring loading is still in the extruder tool, but is locked down to dissallow movement. | The spring loading would have worked given enough structural support around the heatsink. This was impossible due to the heatsink design. | The spring loading did not work as intended.
Component | Type | Development group
Freeform slicer | Software | Novia
Problem | Solution | Implementation
There is no widely available way to turn 3D models into freeform machine code. | A program is required to create freeform models. | A parametric freeform slicer was written from scratch in Javascript. The slicer utilizes the three.js library for 3D rendering. The slicer is capable of calculating the relative coordinates, filament flowrate and hot-end angles for a given path. The slicer outputs the model as G-Code which can be run in the robot program, or on a conventional 3D printer.
Result | What went right? | What went wrong/Could be improved?
The freeform slicer was used for all the freeform prints made in the project, as well as used for virtual illustrations of freeform prints. | The generated models worked extremely well with the robot, with no serious issues or robot crashes. | The program is difficult to use, as all the models are created mathematically as opposed from being created from existing 3D models.
Component | Type | Development group
Extruder interface | Software | Novia
Problem | Solution | Implementation
The extruder firmware is relatively complex and has a number of configurable variables. Often, these variables need to be configured while by-passing the robot control program. | A simple extruder control program is required to more easily interface with the extruder tool. | An extruder interface program was written in Python. The program uses a USB to RS232 adapter to interface directly with the extruder microcontroller. The interface shows detailed sensor data from the microcontroller, and allows for manual control over the extruder. The extruder can be calibrated using the program.
Result | What went right? | What went wrong/Could be improved?
The extruder interface was developed and used extensively within the project. | The extruder interface has been invaluable in debugging, developing and calibrating the extruder. It has also been useful when doing quick work like changing the extruder filament. | We kept having to update the program as the robot communication protocol kept updating.
Component | Type | Development group
Conveyor integration | Hardware | Novia
Problem | Solution | Implementation
The printed objects must fit inside the build volume. | The print volume can be extended by adding a moving conveyor as an additional axis. | A Silverbelt conveyor belt was adapted for use with the RAM platform through the installation of an adapter which would allow it to be connected to the extruder microcontroller.
Result | What went right? | What went wrong/Could be improved?
The conveyor belt could be controlled through the extruder microcontroller. | The conveyor belt works well in tests. | Lack of documentation of the conveyor belt interior caused difficulties when implementing the controller firmware.
Component | Type | Development group
Screw extruder tool | Hardware | VAMK
Problem | Solution | Implementation
Filament extruders have a limited heating and filament flowrate. | Another type of extruder tool can be designed for large-volume printing. | A screw extruder was assembled from
Result | What went right? | What went wrong/Could be improved?
The extruder was successfully assembled and tested. | The screw extruder worked well with the robot and in simulations. | The motor overheated and burnt itself before any prints could be created. A gearbox would be required for future tests to ensure the motor can handle turning the screw.
Component | Type | Development group
Heated build platform | Hardware | VAMK
Problem | Solution | Implementation
Due to thermoplastic warping, printing large-scale objects can be quite challenging. The larger the objects are, the more they warp and the greater the likelyhood that the object will detach from the build surface. | A large-scale and heated build platform is required to prevent plastic warping. | Several build platforms were developed and tested in the project. The first one was a platform intended for robots, with a glass plate. The latest version of the build platform is made from a large aluminum block, heated by thermostat controlled heating pads, with a large glass plate with a BuildTak top layer.
Result | What went right? | What went wrong/Could be improved?
While the first few "cold" platform worked well for small objects, the lack of heating caused significantly larger objects to very often fail and pop off the platform. This was such an issue that we took special precautions during the 3D design process to circumvent the issue. The heated build platform solved these issues and allowed printing of very large-scale objects without issues. | The heated build platform works very well for keeping the printed objects in place, when when the objects are very large. Objects more than a kilogram in weight and over 60x60 centimerers wide have been created without issues. | We should have created a smaller heated build platform earlier in the project, as this would have prevented a lot of failed prints.
Component | Type | Development group
Filament guide | Hardware | UWASA
Problem | Solution | Implementation
The filament strand must remain tight at all times. If the filament gets too loose it will may cause the filament spool to unwind itself and get into a tangle, but if too tight the extruder motor will be unable to pull in new filament. In the worst case, this may cause the filament to get stuck and damage the extruder tool or robot. | Some form of filament guide is required to prevent filament tangling. | Two types of filament guides were designed and tested. One using a single plastic guide, and another using ball bearings to guide the strand of filament.
Result | What went right? | What went wrong/Could be improved?
The ball bearing based filament guide is attached next to the spool holder, and provides a robust and smooth way to feed the filament to the extruder tool. | The filament guide allows the filament to be cut from the extruder tool without risking tangles, as the filament is held inside the guide at all times. | The filament guide could have been made smaller.
Component | Type | Development group
Spool holder | Hardware | UWASA
Problem | Solution | Implementation
The filament spools needs to be located somewhere safe near the robot, where the filament won't get in the way of the robot but won't be far enough away to cause a significant resistance for the extruder motor. | A spool holder of some form is needed. | Spool holders for both small and large spools were designed. The spool holders latches to the robot enclosure walls.
Result | What went right? | What went wrong/Could be improved?
Spool holders of two sizes are next to the robot. They can be used to hold two different types of filament spools. | The spool holders have held up and not broken once. | The spool holders could use ball bearings for smoother rolling.
Component | Type | Development group
Extruder holder | Hardware | Novia
Problem | Solution | Implementation
Due to frequent tool changes, the extruder tools are often moved and stored suboptimally. | Some place to put the extruder when not in use would be beneficial. | A basic extruder holder was created based on the tool changer plate and pin design. The holders can be latched to the walls of the robot enclosure and the tool mounting plates with attached pins rests on top of the holders.
Result | What went right? | What went wrong/Could be improved?
We have several extruder holder for both the extruder tools. The holders are next to the robot and provides a convenient long-term storage for the extruder tools. | The holders are surprisingly robust, and can even hold very heavy tools. | The holders could be made to look nicer.